## Overview
f | Overview
The following Spreadsheet Tab Lists all MBT Products that may be produced in creating a blueprint
When performing Step 6, use the list to communicate the Enterprise Architecture Team to:
Keep track of what products will be delivered
Track what file names represent what products and when provided to EA Team
Communicate the status of a product to the EA Team
Communicate the EA Repository Status of the product to the blueprint Team
Use the Collapse/Group Capability on left to collapse/expand rows
Columns
|  | Methodology for Business Transformation v1.5 | Method Version
|  | Predecessor | Step/Product that this deliverable is dependent on
|  | Predecessor Name | Name of Step/Product that this deliverable is dependent on
|  | LOE | Estimated Level of Effort
|  | Level | Is this a Phase, Step, Activity, or Product
|  | Phase | What is the Parent Phase
|  | Step | What is the Parent Step
|  | Activity | What is the Parent Activity
|  | Type | Is the Product a Document, Diagram, or Information
|  | SubType | If a Document, what is the document type (Presentation, Charter, etc.)
|  | Detail | Relative to the Domain, what is the Level of Detail of this Document, Hi, Medium, Low
|  | Governance | In General, which Governance domain is of most interest - Business or IT
|  | Category | What FEA Category of Product does this Represent?
|  | What is needed for Step 6 | What to do for Step 6 with this Product
|  | Date Submitted | Use to Track when received product
|  | Load Status | Use to Track when loaded product
|  | Review Comments | Use to Track notes on product interaction
Step 6 Load Notes:
If multiple files, provide in a zipped file and refer to such in the spreadsheet
If did not or plan on not creating a MBT Product, mark the status of the Product as "NA"
Finally, working with other frameworks
Working with FEA
Shows all MBT Products as categorized by FEA Categories and MBT Step
Working with All to MBT
Converting DODAF or Zachman to fit into MBT
Working with DODAF
Shows DODAF as compared to Zachman Framework
Working with Zachman
Shows DODAF as compared to Zachman Framework

## Artifact List
Methodology for Business Transformation v1.5 | Predecessor | Predecessor Name | LOE | Level | Phase | Step | Activity | Type | SubType | Level of Detail | Governance | Category | What is needed for Step 6 | Date Submitted | Load Status | Review Comments
Phase 1: Select the Business Areas to Blueprint |  |  | 15 days | Phase | 1 | 0 | 0
Step A: Prioritize and select business areas to blueprint |  |  | 15 days | Step | 1 | A | 0
Define/Validate the enterprise’s business areas |  |  | 5 days | Activity | 1 | A | 1
Business Areas Visual | 4 | Define/Validate the enterprise’s business areas | 0 days | Product | 1 | A | 1 | Document | End Product | H | Business | Business | Provide URL to link to
Define/Validate the criteria for evaluating the business areas to Blueprint |  |  | 5 days | Activity | 1 | A | 2
Business Areas Scoring Template | 6 | Define/Validate the criteria for evaluating the business areas to Blueprint | 0 days | Product | 1 | A | 2 | Document | End Product | H | Business | Business | Provide URL to link to
Evaluate the business areas and select candidates to Blueprint | 4,7 | Define/Validate the enterprise’s business areas | 5 days | Activity | 1 | A | 3
Business Areas Scoring | 8 | Evaluate the business areas and select candidates to Blueprint | 0 days | Product | 1 | A | 3 | Information |  | H | Business | Business | Supporting Data in Spreadsheet
Business Areas Prioritization Chart | 8 | Evaluate the business areas and select candidates to Blueprint | 0 days | Product | 1 | A | 3 | Document | End Product | H | Business | Business | Provide URL to link to
Present the candidates and obtain executive approval to Blueprint | 8 | Evaluate the business areas and select candidates to Blueprint | 5 days | Activity | 1 | A | 4
Business Areas Prioritization Presentation | 11 | Present the candidates and obtain executive approval to Blueprint | 0 days | Product | 1 | A | 4 | Document | Presentation | H | Business | Business | Provide URL to link to
Record of Decision for Business Area to Blueprint | 11 | Present the candidates and obtain executive approval to Blueprint | 0 days | Product | 1 | A | 4 | Document | ROD | H | Business | Business | Provide URL to link to
Enterprise Transition Strategy | 11 | Present the candidates and obtain executive approval to Blueprint | 0 days | Product | 1 | A | 4 | Document | End Product | H | Business | Enterprise | Provide URL to link to
Phase 2: Prepare for the Blueprint |  |  | 80 days | Phase | 2 | 0 | 0
Step B: Identify Ownership and Executive Sponsor |  |  | 5 days | Step | 2 | B | 0
Communicate to leadership the projected time and resource commitments for the study | 14 | Enterprise Transition Strategy | 5 days | Activity | 2 | B | 1
Reach a decision on who will be the Executive Sponsor for the study | 14 | Enterprise Transition Strategy | 5 days | Activity | 2 | B | 2
Perform a more detailed training session for the leadership | 14 | Enterprise Transition Strategy | 5 days | Activity | 2 | B | 3
Develop purpose statement for the Blueprint | 14 | Enterprise Transition Strategy | 5 days | Activity | 2 | B | 4
Blueprint Purpose Statement | 20 | Develop purpose statement for the Blueprint | 0 days | Product | 2 | B | 4 | Document | End Product | H | Business | Performance | Provide URL to link to
Step C: Form the Core Team |  |  | 75 days | Step | 2 | C | 0
Executive Sponsor solicits Core Team members | 21 | Blueprint Purpose Statement | 30 days | Activity | 2 | C | 1
Core Team Solicitation Memorandum | 23 | Executive Sponsor solicits Core Team members | 0 days | Product | 2 | C | 1 | Document | Memo | H | Business | Management | Provide URL to link to
Establish the Core Team Lead | 24 | Core Team Solicitation Memorandum | 15 days | Activity | 2 | C | 2
Core Team Formation Memorandum | 25 | Establish the Core Team Lead | 0 days | Product | 2 | C | 2 | Document | Memo | H | Business | Management | Provide URL to link to
Provide the Core Team with an orientation | 26 | Core Team Formation Memorandum | 5 days | Activity | 2 | C | 3
Create and sign Commitment Agreement | 27 | Provide the Core Team with an orientation | 25 days | Activity | 2 | C | 4
Core Team Commitment Agreement | 28 | Create and sign Commitment Agreement | 0 days | Product | 2 | C | 4 | Document | End Product | H | Business | Management | Provide URL to link to
Phase 3: Complete the Blueprint |  |  | 305 days | Phase | 3 | 0 | 0
Step 1: Perform Blueprint Project Management |  |  | 55 days | Step | 3 | 1 | 0
Establish the Core Team Charter |  |  | 30 days | Activity | 3 | 1 | 1
Core Team Charter | 32 | Establish the Core Team Charter | 0 days | Product | 3 | 1 | 1 | Document | Charter | H | Business | Management | Provide URL to link to
Establish the communications strategy for the Blueprint | 32 | Establish the Core Team Charter | 25 days | Activity | 3 | 1 | 2
Communications Strategy | 34 | Establish the communications strategy for the Blueprint | 0 days | Product | 3 | 1 | 2 | Document | PMO | H | Business | Management | Provide URL to link to
Communications Plan | 35 | Communications Strategy | 0 days | Product | 3 | 1 | 2 | Document | Plan | H | Business | Management | Provide URL to link to
Establish the project plan for the Blueprint |  |  | 20 days | Activity | 3 | 1 | 3
Blueprint Project Plan | 37 | Establish the project plan for the Blueprint | 0 days | Product | 3 | 1 | 3 | Document | Plan | H | Business | Management | Provide URL to link to
Step 2: Analyze stakeholders / drivers and define the target business strategy |  |  | 95 days | Step | 3 | 2 | 0
Determine and prioritize business area stakeholders and drivers | 37 | Establish the project plan for the Blueprint | 5 days | Activity | 3 | 2 | 1
Stakeholder Hierarchy Diagram and Prioritized List | 40 | Determine and prioritize business area stakeholders and drivers | 0 days | Product | 3 | 2 | 1 | Diagram |  | H | Business | Performance | Diagram in MBT Template File
Business Drivers/Mandates Hierarchy Diagram and Prioritized List | 40 | Determine and prioritize business area stakeholders and drivers | 0 days | Product | 3 | 2 | 1 | Diagram |  | H | Business | Performance | Diagram in MBT Template File
Conduct stakeholder interviews to determine needs | 40 | Determine and prioritize business area stakeholders and drivers | 30 days | Activity | 3 | 2 | 2
Stakeholder Exchange Diagrams | 43 | Conduct stakeholder interviews to determine needs | 0 days | Product | 3 | 2 | 2 | Diagram |  | M | Business | Performance | Diagram in MBT Template File
SWOT Diagram | 43 | Conduct stakeholder interviews to determine needs | 0 days | Product | 3 | 2 | 2 | Diagram |  | M | Business | Performance | Diagram in MBT Template File
Perform Organizational Readiness Assessment | 40 | Determine and prioritize business area stakeholders and drivers | 10 days | Activity | 3 | 2 | 3
Organizational Readiness Assessment | 46 | Perform Organizational Readiness Assessment | 0 days | Product | 3 | 2 | 3 | Document | End Product | M | Business | Performance | Provide URL to link to
Define the business area vision based on stakeholder needs and drivers | 43,46 | Conduct stakeholder interviews to determine needs | 5 days | Activity | 3 | 2 | 4
Vision Document | 48 | Define the business area vision based on stakeholder needs and drivers | 0 days | Product | 3 | 2 | 4 | Document | End Product | H | Business | Performance | Provide URL to link to
Document and baseline goals/objectives and map to parent organization's goals/objectives | 48 | Define the business area vision based on stakeholder needs and drivers | 20 days | Activity | 3 | 2 | 5
Goals and Objectives Hierarchy Diagram with Baseline Data | 50 | Document and baseline goals/objectives and map to parent organization's goals/objectives | 0 days | Product | 3 | 2 | 5 | Diagram |  | M | Business | Performance | Diagram in MBT Template File Supporting Data in Spreadsheet
Business Area Goals and Objectives to Parent Organization's Goals and Objectives Matrix | 50 | Document and baseline goals/objectives and map to parent organization's goals/objectives | 0 days | Product | 3 | 2 | 5 | Information |  | M | Business | Performance | Supporting Data in Spreadsheet
Business Area Balanced Scorecard | 50 | Document and baseline goals/objectives and map to parent organization's goals/objectives | 0 days | Product | 3 | 2 | 5 | Information |  | H | Business | Performance | Supporting Data in Spreadsheet
Business Area Strategy to Mandates Matrix | 50 | Document and baseline goals/objectives and map to parent organization's goals/objectives | 0 days | Product | 3 | 2 | 5 | Information |  | M | Business | Performance | Supporting Data in Spreadsheet
Define business products and services and target maturity levels | 50 | Document and baseline goals/objectives and map to parent organization's goals/objectives | 30 days | Activity | 3 | 2 | 6
Business Area Products and Services Maturity Model | 55 | Define business products and services and target maturity levels | 0 days | Product | 3 | 2 | 6 | Information |  | M | Business | Performance | Supporting Data in Spreadsheet
Formulate business strategy results and brief to governance teams | 55 | Define business products and services and target maturity levels | 5 days | Activity | 3 | 2 | 7
Presentation on Business Area Strategy and Product and Services | 57 | Formulate business strategy results and brief to governance teams | 0 days | Product | 3 | 2 | 7 | Document | Presentation | H | Business | Performance | Provide URL to link to
Step 3: Analyze the business and define the target business environment |  |  | 60 days | Step | 3 | 3 | 0
Determine the value chain for the business area | 57 | Formulate business strategy results and brief to governance teams | 5 days | Activity | 3 | 3 | 1
As-Is Value Chain Diagram | 60 | Determine the value chain for the business area | 0 days | Product | 3 | 3 | 1 | Diagram |  | H | Business | Business | Diagram in MBT Template File
Target Value Chain Diagram | 60 | Determine the value chain for the business area | 0 days | Product | 3 | 3 | 1 | Diagram |  | H | Business | Business | Diagram in MBT Template File
Decompose the business function model | 60 | Determine the value chain for the business area | 5 days | Activity | 3 | 3 | 2
As-Is Business Function Model | 63 | Decompose the business function model | 0 days | Product | 3 | 3 | 2 | Diagram |  | M | Business | Business | Diagram in MBT Template File
Target Business Function Model | 63 | Decompose the business function model | 0 days | Product | 3 | 3 | 2 | Diagram |  | M | Business | Business | Diagram in MBT Template File
Analyze the current processes and their performance | 65 | Decompose the business function model | 15 days | Activity | 3 | 3 | 3
Existing Investments to Business Processes Matrix | 67 | Analyze the current processes and their performance | 0 days | Product | 3 | 3 | 3 | Information |  | M | Business | Business | Supporting Data in Spreadsheet
As-Is IDEF0 Diagrams for Critical Value Chain Processes | 67 | Analyze the current processes and their performance | 0 days | Product | 3 | 3 | 3 | Diagram |  | M | Business | Business | Diagram in MBT Template File
As-Is Swim Lane Diagram (actual organization) |  | Analyze the current processes and their performance | 0 days | Product | 3 | 3 | 3 | Diagram |  | M | Business | Business | Diagram in MBT Template File
Define key target processes / data and their target performance | 67 | Analyze the current processes and their performance | 25 days | Activity | 3 | 3 | 4
Target IDEF0 Diagrams for Critical Value Chain Processes | 70 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Diagram |  | M | Business | Business | Diagram in MBT Template File
Target Swim Lane Diagram (proposed organizations) | 71 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Diagram |  | M | IT | Business | Diagram in MBT Template File
Target Data Stewardship Matrix | 70 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Information |  | M | IT | Data | Supporting Data in Spreadsheet
Target Information Services Matrix |  | Target IDEF0 Diagrams for Critical Value Chain Processes | 0 days | Product | 3 | 3 | 4 | Information |  | M | IT | Data | Supporting Data in Spreadsheet
Entity Relationship Diagram | 70 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Diagram |  | M | IT | Data | Diagram in MBT Template File
Target Logical Data Model | 70 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Diagram |  | L | IT | Data | Supporting Data in Spreadsheet
Target Business Process to Data Entity CRUD Matrix | 70 | Define key target processes / data and their target performance | 0 days | Product | 3 | 3 | 4 | Information |  | M | IT | Data | Supporting Data in Spreadsheet
Formulate the business analysis results and brief to governance teams | 70 | Define key target processes / data and their target performance | 10 days | Activity | 3 | 3 | 5
Business and Data Analysis Presentation | 77 | Formulate the business analysis results and brief to governance teams | 0 days | Product | 3 | 3 | 5 | Document | Presentation | H | Business | Management | Provide URL to link to
Step 4: Analyze the IT and develop the target conceptual solution architecture |  |  | 85 days | Step | 3 | 4 | 0
Assess and score the existing IT portfolio | 39 | Step 2: Analyze stakeholders / drivers and define the target business strategy | 45 days | Activity | 3 | 4 | 1
As-Is BFA Portfolio Assessment | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | M | IT | Services | Supporting Data in Spreadsheet
Initial Business Focus Area Metadata | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | L | IT | Services | Supporting Data in Spreadsheet
As-Is System Interface Diagram | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Diagram |  | M | IT | Services | Diagram in MBT Template File
Systems and Services Description and Scoring (As-Is) | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | M | IT | Services | Supporting Data in Spreadsheet
Total Cost of Ownership | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | M | IT | Services | Supporting Data in Spreadsheet
Enterprise Architecture Repository Portfolio Reports | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Document | End Product | L | IT | Services | Provide URL to link to
As-Is Data Store to Target Logical Data Model Entity Matrix | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | L | IT | Data | Supporting Data in Spreadsheet
As-Is Data Store ADS Assessment Matrix | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | L | IT | Data | Supporting Data in Spreadsheet
ADS Scoring Summary | 80 | Assess and score the existing IT portfolio | 0 days | Product | 3 | 4 | 1 | Information |  | M | IT | Data | Supporting Data in Spreadsheet
Develop the target conceptual solution architecture | 78 | Business and Data Analysis Presentation | 10 days | Activity | 3 | 4 | 2
Systems and Services Description and Scoring (Target) | 90 | Develop the target conceptual solution architecture | 0 days | Product | 3 | 4 | 2 | Information |  | M | IT | Services | Supporting Data in Spreadsheet
Integrated Target Services and Systems Model | 90 | Develop the target conceptual solution architecture | 0 days | Product | 3 | 4 | 2 | Diagram |  | M | IT | Services | Diagram in MBT Template File
Solution Architecture Document | 90 | Develop the target conceptual solution architecture | 0 days | Product | 3 | 4 | 2 | Document | End Product | L | IT | Services | Provide URL to link to
Verify the target conceptual solution architecture complies with the EA | 90 | Develop the target conceptual solution architecture | 5 days | Activity | 3 | 4 | 3
Determine the gaps between the current IT portfolio and the target | 94 | Verify the target conceptual solution architecture complies with the EA | 5 days | Activity | 3 | 4 | 4
Architecture Decision Document | 95 | Determine the gaps between the current IT portfolio and the target | 0 days | Product | 3 | 4 | 4 | Document | ROD | M | IT | Services | Provide URL to link to
Formulate the IT analysis results and brief to governance teams | 95 | Determine the gaps between the current IT portfolio and the target | 5 days | Activity | 3 | 4 | 5
Presentation on Systems, Services, and Investments Analysis | 97 | Formulate the IT analysis results and brief to governance teams | 0 days | Product | 3 | 4 | 5 | Document | Presentation | H | Business | Services | Provide URL to link to
Step 5: Author the Modernization Blueprint and obtain governance approvals |  |  | 75 days | Step | 3 | 5 | 0
Define findings, recommendations and implementation alternatives | 98,74 | Entity Relationship Diagram | 20 days | Activity | 3 | 5 | 1
Modernization Recommendations to Horizontal Dependencies Matrix | 100 | Define findings, recommendations and implementation alternatives | 0 days | Product | 3 | 5 | 1 | Information |  | M | Business | Management | Supporting Data in Spreadsheet
Modernization Recommendations to Mandates Matrix | 100 | Define findings, recommendations and implementation alternatives | 0 days | Product | 3 | 5 | 1 | Information |  | M | Business | Performance | Supporting Data in Spreadsheet
Modernization Blueprint Findings, Recommendations, and Alternatives Presentation | 100 | Define findings, recommendations and implementation alternatives | 0 days | Product | 3 | 5 | 1 | Document | Presentation | H | Business | Management | Provide URL to link to
Apply the VMM to the alternatives and select the proposed implementation alternatives | 100 | Define findings, recommendations and implementation alternatives | 15 days | Activity | 3 | 5 | 2
Value Measuring Methodology Cost to Value Matrix | 104 | Apply the VMM to the alternatives and select the proposed implementation alternatives | 0 days | Product | 3 | 5 | 2 | Information |  | M | Business | Management | Supporting Data in Spreadsheet
Validate the proposed implementation alternatives with governance teams | 104 | Apply the VMM to the alternatives and select the proposed implementation alternatives | 10 days | Activity | 3 | 5 | 3
Author draft Modernization Blueprint including transition documentation | 98 | Presentation on Systems, Services, and Investments Analysis | 20 days | Activity | 3 | 5 | 4
Draft Recommendation Implementation Overview Visual | 107 | Author draft Modernization Blueprint including transition documentation | 0 days | Product | 3 | 5 | 4 | Document | End Product | H | Business | Management | Provide URL to link to
Draft Strategic Systems Migration Diagram | 107 | Author draft Modernization Blueprint including transition documentation | 0 days | Product | 3 | 5 | 4 | Diagram |  | M | Business | Services | Diagram in MBT Template File
Draft Strategic Sequencing Overview Visual | 107 | Author draft Modernization Blueprint including transition documentation | 0 days | Product | 3 | 5 | 4 | Document | End Product | H | Business | Management | Provide URL to link to
Draft Implementation Sequencing Plan | 107 | Author draft Modernization Blueprint including transition documentation | 0 days | Product | 3 | 5 | 4 | Document | Plan | L | Business | Management | Provide URL to link to
Draft Modernization Blueprint | 107 | Author draft Modernization Blueprint including transition documentation | 0 days | Product | 3 | 5 | 4 | Document | End Product | M | Business | Management | Provide URL to link to
Distribute Modernization Blueprint and incorporate feedback | 107 | Author draft Modernization Blueprint including transition documentation | 45 days | Activity | 3 | 5 | 5
Final Recommendation Implementation Overview Visual | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | End Product | H | Business | Management | Provide URL to link to
Final Strategic Systems Migration Diagram | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Diagram |  | M | Business | Services | Diagram in MBT Template File
Final Strategic Sequencing Overview Visual | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | End Product | H | Business | Management | Provide URL to link to
Final Implementation Sequencing Plan | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | Plan | L | Business | Management | Provide URL to link to
Final Modernization Blueprint | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | End Product | M | Business | Management | Provide URL to link to
Business and Stakeholder Interaction Log | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | PMO | L | Business | Management | Provide URL to link to
Feedback Tracking Document and Feedback Action Report | 113 | Distribute Modernization Blueprint and incorporate feedback | 0 days | Product | 3 | 5 | 5 | Document | PMO | L | Business | Management | Provide URL to link to
Brief key stakeholders and governance teams, obtain approval, and publish Blueprint | 113 | Distribute Modernization Blueprint and incorporate feedback | 10 days | Activity | 3 | 5 | 6
Modernization Blueprint Presentation | 121 | Brief key stakeholders and governance teams, obtain approval, and publish Blueprint | 0 days | Product | 3 | 5 | 6 | Document | Presentation | H | Business | Management | Provide URL to link to
Record of Decision | 121 | Brief key stakeholders and governance teams, obtain approval, and publish Blueprint | 0 days | Product | 3 | 5 | 6 | Document | ROD | H | Business | Management | Provide URL to link to
Step 6: Incorporate approved Modernization Blueprint into enterprise architecture |  |  | 30 days | Step | 3 | 6 | 0
Load target architecture data from approved Modernization Blueprint into EA Repository | 121 | Brief key stakeholders and governance teams, obtain approval, and publish Blueprint | 30 days | Activity | 3 | 6 | 1
Blueprint Products Loaded | 125 | Load target architecture data from approved Modernization Blueprint into EA Repository | 0 days | Product | 3 | 6 | 1 | Diagram |  | L | IT | Enterprise | Diagram in MBT Template File
Business Focus Area Metadata Loaded | 125 | Load target architecture data from approved Modernization Blueprint into EA Repository | 0 days | Product | 3 | 6 | 1 | Information |  | L | IT | Enterprise | Supporting Data in Spreadsheet
Update enterprise level products | 121 | Brief key stakeholders and governance teams, obtain approval, and publish Blueprint | 5 days | Activity | 3 | 6 | 2
Enterprise Data Exchange Node Drawing | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Diagram |  | M | IT | Data | Diagram in MBT Template File
Enterprise Data Stewardship Matrix | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Information |  | H | IT | Data | Supporting Data in Spreadsheet
Enterprise Modernization Sequencing Plan | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Document | Plan | L | IT | Management | Provide URL to link to
Enterprise Modernization Dependencies Matrix | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Information |  | M | IT | Management | Supporting Data in Spreadsheet
Enterprise Horizontal Services Model | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Diagram |  | M | IT | Services | Diagram in MBT Template File
Enterprise Modernization Recommendations to Mandates Matrix | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Information |  | M | IT | Performance | Supporting Data in Spreadsheet
Enterprise Modernization Recommendations to Outcomes Matrix | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Information |  | M | IT | Performance | Supporting Data in Spreadsheet
Department Reference Models | 128 | Update enterprise level products | 0 days | Product | 3 | 6 | 2 | Diagram |  | L | IT | Enterprise | Diagram in MBT Template File
Brief the governance teams on the updated enterprise level products | 128 | Update enterprise level products | 5 days | Activity | 3 | 6 | 3
Publish updated enterprise products | 137 | Brief the governance teams on the updated enterprise level products | 2 days | Activity | 3 | 6 | 4
Published Enterprise Products | 138 | Publish updated enterprise products | 0 days | Product | 3 | 6 | 4 | Document | End Product | L | IT | Enterprise | Provide URL to link to
Update the Enterprise Transition Strategy | 139 | Published Enterprise Products | 5 days | Activity | 3 | 6 | 5
Updated Enterprise Transition Strategy | 140 | Update the Enterprise Transition Strategy | 0 days | Product | 3 | 6 | 5 | Document | End Product | M | Business | Enterprise | Provide URL to link to
Phase 4: Implement the Blueprint Recommendations |  |  | 1025 days | Phase | 4 | 0 | 0
Step 7: Perform business transformation initiation tasks |  |  | 25 days | Step | 4 | 7 | 0
Form Core Modernization Implementation Team (CMIT) with representatives from sponsor business areas | 124 | Step 6: Incorporate approved Modernization Blueprint into enterprise architecture | 5 days | Activity | 4 | 7 | 1
Revise Core Modernization Implementation Team Charter Including Roster | 144 | Form Core Modernization Implementation Team (CMIT) with representatives from sponsor business areas | 0 days | Product | 4 | 7 | 1 | Document | Charter | H | Business | Management | Provide URL to link to
Develop Project Plan revisions based on IRB priorities and resource commitments | 144 | Form Core Modernization Implementation Team (CMIT) with representatives from sponsor business areas | 5 days | Activity | 4 | 7 | 2
Update BFA Transition Plan (derived from Blueprint Transistion Plan) | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 0 days | Product | 4 | 7 | 2 | Document | Plan | M | Business | Management | Provide URL to link to
Integrate with IEA Enterprise Modernization Sequencing Plan | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 0 days | Product | 4 | 7 | 2 | Document | Plan | L | Business | Management | Provide URL to link to
Develop Funding Strategy |  |  | 5 days | Activity | 4 | 7 | 3
Based on program plan, develop funding and resources strategy for modernization | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 5 days | Activity | 4 | 7 | 4
Funding and Resource Strategy Document | 150 | Based on program plan, develop funding and resources strategy for modernization | 0 days | Product | 4 | 7 | 4 | Document | Business Case | M | Business | Management | Provide URL to link to
Develop Communications Plan |  |  | 5 days | Activity | 4 | 7 | 5
Develop Communications and Outreach Strategy for Implementation | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 5 days | Activity | 4 | 7 | 6
Revise Communications Plan | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 5 days | Activity | 4 | 7 | 7
Revise Program Website | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 5 days | Activity | 4 | 7 | 8
Develop Risk and Change Management Strategies | 146 | Develop Project Plan revisions based on IRB priorities and resource commitments | 5 days | Activity | 4 | 7 | 9
Risk Management / Mitigation Plan | 156 | Develop Risk and Change Management Strategies | 0 days | Product | 4 | 7 | 9 | Document | Plan | M | Business | Management | Provide URL to link to
Change Management Plan | 156 | Develop Risk and Change Management Strategies | 0 days | Product | 4 | 7 | 9 | Document | Plan | M | Business | Management | Provide URL to link to
Communicate Risk and Change Management to Stakeholders | 152,156 | Develop Communications Plan | 5 days | Activity | 4 | 7 | 10
Brief IBAT/IRB/CTOC on program plan, program status, funding strategy, resource strategy | 159 | Communicate Risk and Change Management to Stakeholders | 5 days | Activity | 4 | 7 | 11
Modernization Program Status Briefing | 160 | Brief IBAT/IRB/CTOC on program plan, program status, funding strategy, resource strategy | 0 days | Product | 4 | 7 | 11 | Document | PMO | H | Business | Management | Provide URL to link to
Step 8: Conduct Business Process Reengineering (as necessary) |  |  | 95 days | Step | 4 | 8 | 0
BPR planning | 143 | Step 7: Perform business transformation initiation tasks | 5 days | Activity | 4 | 8 | 1
BPR Team Membership Roster Document | 163 | BPR planning | 0 days | Product | 4 | 8 | 1 | Document | PMO | H | Business | Management | Provide URL to link to
BPR Scope Document | 163 | BPR planning | 0 days | Product | 4 | 8 | 1 | Document | End Product | M | Business | Business | Provide URL to link to
Create/refine (as-is) process baseline | 163 | BPR planning | 30 days | Activity | 4 | 8 | 2
Normalized As-Is IDEF0 Diagrams | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Diagram |  | L | IT | Business | Diagram in MBT Template File
Updated BFA BRM Hierarchy Diagram (if applicable) | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Diagram |  | L | IT | Business | Diagram in MBT Template File
Updated Conceptual Data Model (if applicable) | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Diagram |  | M | IT | Business | Diagram in MBT Template File
Updated Conceptual Data Model to Business Function Matrix (if applicable) | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Information |  | L | IT | Business | Supporting Data in Spreadsheet
Updated Conceptual Data Entity Stewardship Matrix (if applicable) | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Information |  | M | IT | Business | Supporting Data in Spreadsheet
Updated BFA As-Is Services and Systems Diagram (if applicable) | 166 | Create/refine (as-is) process baseline | 0 days | Product | 4 | 8 | 2 | Diagram |  | M | IT | Business | Diagram in MBT Template File
Research and benchmarking | 166 | Create/refine (as-is) process baseline | 30 days | Activity | 4 | 8 | 3
Recommendations and Findings for Process Improvement Document | 173 | Research and benchmarking | 0 days | Product | 4 | 8 | 3 | Information |  | H | IT | Business | Supporting Data in Spreadsheet
Develop the future (to-be) process | 173 | Research and benchmarking | 30 days | Activity | 4 | 8 | 4
Normalized As-Is IDEF0 Diagrams | 175 | Develop the future (to-be) process | 0 days | Product | 4 | 8 | 4 | Diagram |  | L | IT | Business | Diagram in MBT Template File
Updated BFA To-Be Services and Systems Diagram (if applicable) | 175 | Develop the future (to-be) process | 0 days | Product | 4 | 8 | 4 | Diagram |  | M | IT | Business | Diagram in MBT Template File
Updated BFA Data Standards Document (if applicable) | 175 | Develop the future (to-be) process | 0 days | Product | 4 | 8 | 4 | Document | End Product | M | IT | Business | Provide URL to link to
Recommendations and Findings Presentation | 175 | Develop the future (to-be) process | 0 days | Product | 4 | 8 | 4 | Document | Presentation | H | Business | Business | Provide URL to link to
Step 9: Conduct data standardization |  |  | 135 days | Step | 4 | 9 | 0
Review Blueprint and BPR References | 162 | Step 8: Conduct Business Process Reengineering (as necessary) | 5 days | Activity | 4 | 9 | 1
Logical Data Model | 181 | Review Blueprint and BPR References | 0 days | Product | 4 | 9 | 1 | Diagram |  | L | IT | Data | Diagram in MBT Template File
Identify Data Requirements and Develop Data Standards | 181 | Review Blueprint and BPR References | 15 days | Activity | 4 | 9 | 2
Data Proposal Package | 183 | Identify Data Requirements and Develop Data Standards | 0 days | Product | 4 | 9 | 2 | Document | End Product | L | Business | Data | Provide URL to link to
Review and Adopt Data Standards | 183 | Identify Data Requirements and Develop Data Standards | 25 days | Activity | 4 | 9 | 3
Adopted or Rejected DOI Data Standards | 185 | Review and Adopt Data Standards | 0 days | Product | 4 | 9 | 3 | Document | End Product | L | IT | Data | Provide URL to link to
Possible Changes to a Proposal Package for Resubmission | 185 | Review and Adopt Data Standards | 0 days | Product | 4 | 9 | 3 | Document | End Product | L | IT | Data | Provide URL to link to
Implement Data Standards | 185 | Review and Adopt Data Standards | 90 days | Activity | 4 | 9 | 4
Interior Data Reference Model | 188 | Implement Data Standards | 0 days | Product | 4 | 9 | 4 | Diagram |  | L | IT | Data | Diagram in MBT Template File
XML Tags and Schemas | 188 | Implement Data Standards | 0 days | Product | 4 | 9 | 4 | Diagram |  | L | IT | Data | Diagram in MBT Template File
Information Exchange Packages | 188 | Implement Data Standards | 0 days | Product | 4 | 9 | 4 | Diagram |  | L | IT | Data | Diagram in MBT Template File
Physical Database Schemas | 188 | Implement Data Standards | 0 days | Product | 4 | 9 | 4 | Diagram |  | L | IT | Data | Diagram in MBT Template File
Step 10A: Execute O&M funding strategy for minor recommendations |  |  | 120 days | Step | 4 | 10A | 0
Execute O&M funding strategy for minor recommendations |  |  | 120 days | Activity | 4 | 10A | 1
Step 10B: Incorporate major recommendations into investment request (as necessary) |  |  | 60 days | Step | 4 | 10B | 0
Formulate CPIC pre-select recommendations from Blueprint items funded outside of O&M | 143 | Step 7: Perform business transformation initiation tasks | 20 days | Activity | 4 | 10B | 1
CPIC Pre-Select Documents | 196 | Formulate CPIC pre-select recommendations from Blueprint items funded outside of O&M | 0 days | Product | 4 | 10B | 1 | Document | Business Case | M | Business | Management | Provide URL to link to
Present major recommendations as pre-select candidates to IRB | 196 | Formulate CPIC pre-select recommendations from Blueprint items funded outside of O&M | 5 days | Activity | 4 | 10B | 2
CPIC Pre-Select Presentation to IRB | 198 | Present major recommendations as pre-select candidates to IRB | 0 days | Product | 4 | 10B | 2 | Document | Presentation | H | Business | Management | Provide URL to link to
Author the Exhibit 300 from the approved Blueprint | 198 | Present major recommendations as pre-select candidates to IRB | 20 days | Activity | 4 | 10B | 3
Draft Exhibit 300 | 200 | Author the Exhibit 300 from the approved Blueprint | 0 days | Product | 4 | 10B | 3 | Document | Business Case | M | Business | Management | Provide URL to link to
Brief CMIT on Exhibit 300 and obtain content approval | 200 | Author the Exhibit 300 from the approved Blueprint | 5 days | Activity | 4 | 10B | 4
Updated Draft Exhibit 300 | 202 | Brief CMIT on Exhibit 300 and obtain content approval | 0 days | Product | 4 | 10B | 4 | Document | Business Case | M | Business | Management | Provide URL to link to
Submit Exhibit 300 to CPIC | 202 | Brief CMIT on Exhibit 300 and obtain content approval | 5 days | Activity | 4 | 10B | 5
Updated Draft Exhibit 300 | 204 | Submit Exhibit 300 to CPIC | 0 days | Product | 4 | 10B | 5 | Document | Business Case | M | Business | Management | Provide URL to link to
Obtain approval of Exhibit 300 | 204 | Submit Exhibit 300 to CPIC | 5 days | Activity | 4 | 10B | 6
Approved Exhibit 300 | 206 | Obtain approval of Exhibit 300 | 0 days | Product | 4 | 10B | 6 | Document | Business Case | M | Business | Management | Provide URL to link to
Step 11: Define detailed solution architecture |  |  | 125 days | Step | 4 | 11 | 0
Form solution architecture team (IPT with contracts) | 143 | Step 7: Perform business transformation initiation tasks | 15 days | Activity | 4 | 11 | 1
Solution Architecture Team Roster Document | 209 | Form solution architecture team (IPT with contracts) | 0 days | Product | 4 | 11 | 1 | Document | PMO | H | IT | Management | Provide URL to link to
Define detailed solution architecture | 209 | Form solution architecture team (IPT with contracts) | 60 days | Activity | 4 | 11 | 2
Interior Data Reference Model | 211 | Define detailed solution architecture | 0 days | Product | 4 | 11 | 2 | Diagram |  | L | IT | Enterprise | Diagram in MBT Template File
Detailed Solution Architecture | 211 | Define detailed solution architecture | 0 days | Product | 4 | 11 | 2 | Document | End Product | L | IT | Services | Provide URL to link to
Validate solution architecture against enterprise architecture | 211 | Define detailed solution architecture | 30 days | Activity | 4 | 11 | 3
Submit solution architecture for CMIT approval | 214 | Validate solution architecture against enterprise architecture | 10 days | Activity | 4 | 11 | 4
Submit solution architecture for IBAT/CTOC review | 215 | Submit solution architecture for CMIT approval | 10 days | Activity | 4 | 11 | 5
Step 12: Implement solution and conduct change management tasks |  |  | 570 days | Step | 4 | 12 | 0
Solicit hardware/software/professional services as needed | 208 | Step 11: Define detailed solution architecture | 90 days | Activity | 4 | 12 | 1
Request for Proposal Document | 218 | Solicit hardware/software/professional services as needed | 0 days | Product | 4 | 12 | 1 | Document | Business Case | H | IT | Technology | Provide URL to link to
Proposal Evaluation Criteria Document | 218 | Solicit hardware/software/professional services as needed | 0 days | Product | 4 | 12 | 1 | Document | Business Case | H | IT | Technology | Provide URL to link to
Acquire hardware/software/professional services as needed | 218 | Solicit hardware/software/professional services as needed | 90 days | Activity | 4 | 12 | 2
Evaluated Proposals | 221 | Acquire hardware/software/professional services as needed | 0 days | Product | 4 | 12 | 2 | Document | Business Case | M | IT | Management | Provide URL to link to
Selected Proposal | 221 | Acquire hardware/software/professional services as needed | 0 days | Product | 4 | 12 | 2 | Document | Business Case | M | IT | Management | Provide URL to link to
Implement solution and conduct outreach briefings to management / staff | 221 | Acquire hardware/software/professional services as needed | 360 days | Activity | 4 | 12 | 3
Final Solution Requirements Document | 224 | Implement solution and conduct outreach briefings to management / staff | 0 days | Product | 4 | 12 | 3 | Document | End Product | L | IT | Enterprise | Provide URL to link to
Implemented Solution | 224 | Implement solution and conduct outreach briefings to management / staff | 0 days | Product | 4 | 12 | 3 | Document | End Product | L | Business | Enterprise | Provide URL to link to
Enterprise Level Solution Presentations | 224 | Implement solution and conduct outreach briefings to management / staff | 0 days | Product | 4 | 12 | 3 | Document | Presentation | H | Business | Enterprise | Provide URL to link to
Formulate and issue new policy resulting from solution implementation | 218 | Solicit hardware/software/professional services as needed | 180 days | Activity | 4 | 12 | 4
Policy Memo Document(s) | 228 | Formulate and issue new policy resulting from solution implementation | 0 days | Product | 4 | 12 | 4 | Document | Memo | H | Business | Management | Provide URL to link to
Implement organizational change recommendations | 218 | Solicit hardware/software/professional services as needed | 180 days | Activity | 4 | 12 | 5
Construct and implement training strategy based on BPR and solution architecture | 218 | Solicit hardware/software/professional services as needed | 90 days | Activity | 4 | 12 | 6
Training Strategy/Curriculum Document | 231 | Construct and implement training strategy based on BPR and solution architecture | 0 days | Product | 4 | 12 | 6 | Document | PMO | H | IT | Management | Provide URL to link to
Evaluate solution against its intended purpose | 224 | Implement solution and conduct outreach briefings to management / staff | 30 days | Activity | 4 | 12 | 7
Phase 5: Maintain the Blueprint |  |  | 55 days | Phase | 5 | 0 | 0
Step 13: Maintain the Blueprint and the architecture |  |  | 55 days | Step | 5 | 13 | 0
Author Blueprint Appendix (architecture modification) and submit for CMBT review |  |  | 30 days | Activity | 5 | 13 | 1
Blueprint Appendix (architecture modification) | 236 | Author Blueprint Appendix (architecture modification) and submit for CMBT review | 0 days | Product | 5 | 13 | 1 | Document | End Product | L | IT | Services | Provide URL to link to
Submit Blueprint Appendix (architecture modification) to IBAT/CTOC for review | 236 | Author Blueprint Appendix (architecture modification) and submit for CMBT review | 15 days | Activity | 5 | 13 | 2
Architecture Modification Presentation | 238 | Submit Blueprint Appendix (architecture modification) to IBAT/CTOC for review | 0 days | Product | 5 | 13 | 2 | Document | Presentation | H | IT | Management | Provide URL to link to
Brief the Architecture modifications to IRB and receive approval (if necessary) | 238 | Submit Blueprint Appendix (architecture modification) to IBAT/CTOC for review | 5 days | Activity | 5 | 13 | 3
Architecture Modification Presentation for IRB | 240 | Brief the Architecture modifications to IRB and receive approval (if necessary) | 0 days | Product | 5 | 13 | 3 | Document | Presentation | H | IT | Management | Provide URL to link to
Publish updated Blueprint and architecture artifacts | 240 | Brief the Architecture modifications to IRB and receive approval (if necessary) | 5 days | Activity | 5 | 13 | 4
Updated Architecture Artifacts | 242 | Publish updated Blueprint and architecture artifacts | 0 days | Product | 5 | 13 | 4 | Document | End Product | L | IT | Enterprise | Provide URL to link to
Re-published Blueprint | 242 | Publish updated Blueprint and architecture artifacts | 0 days | Product | 5 | 13 | 4 | Document | End Product | L | Business | Management | Provide URL to link to
Updated DOI Enterprise Artifacts | 242 | Publish updated Blueprint and architecture artifacts | 0 days | Product | 5 | 13 | 4 | Document | End Product | L | Business | Enterprise | Provide URL to link to

## Artifact by FEA Category
Phase | (All)
Level | Product
Count of Methodology for Business Transformation v1.5 | Step
Category | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 11 | 12 | 13 | 10B | A | B | C | Grand Total
Business |  |  | 9 |  |  |  |  | 12 | [5 empty] | 6 |  |  | 27
Data |  |  | 5 | 3 |  | 2 |  |  | 8 | [7 empty] | 18
Enterprise | [5 empty] | 5 |  |  |  | 1 | 3 | 2 |  | 1 |  |  | 12
Management | 4 |  | 1 |  | 15 | 2 | 7 | 1 |  | 1 | 4 | 3 | 6 |  |  | 3 | 47
Performance |  | 12 |  |  | 1 | 2 | [8 empty] | 1 |  | 16
Services |  |  |  | 11 | 2 | 1 |  |  |  | 1 |  | 1 |  |  |  |  | 16
Technology | [10 empty] | 2 | [5 empty] | 2
Grand Total | 4 | 12 | 15 | 14 | 18 | 12 | 7 | 13 | 8 | 3 | 9 | 6 | 6 | 7 | 1 | 3 | 138
Double-Click on a cell to see the Product List

## Re-using DODAF-ZACH with MBT
DODAF View Type | DODAF Product Code | DODAF Product Name | DODAF Product Description | Zachman | CADM Support | General Modeling Techniques (IDEF) | UML Technique | Comments | MBT Step | MBT Work Product | DEAR Element | Corresponding FEA Reference Model
All View | AV-1 | Overview and Summary Information | Details scope, purpose, environment, and other summary-level formation for an architecture description. | Motivation-Scope Model | Document Store | None | No equivalent |  | 2,3 | Vision, Problem Statements, Value Chain, Capabiliteis Maturity Model, Performance Models | Department PRM BFA Vision, Mission and PRM Findings and Recommendations | PRM MISSION Goals, EO/IO operational metrics
All View | AV-2 | Integrated Dictionary | Provides definitions of all terms used in all products. | Data-Detailed Representations Model | Data Dictionary | None | Usually has one |  |  | N/A | Data Dictionary Meta-model Glossary | OMB Guidance for Reference Models
Operational View | OV-1 | Operational Concept Graphic | Provides a graphical and textual description of the operational concept. | Function-Scope Model | Document Store | None | None |  | 2 | Vision Document | Vision Report | PRM
Operational View | OV-2 | Operational Node Connectivity Description. | Lists the operational nodes, activities performed at each node, connectivity, and information needs between nodes. | Network-Scope Model | ?? | Node Line diagram | Collaboration or Operational Node Connectivity Description |  | 2 | Stakeholder /Hierarchy Diagrams and Product and Service Exchange Matrices and Diagrams | Stakeholder Exchange Diagram Stakeholder Category, Stakeholder, ICOM Arrow | BRM, DRM
Operational View | OV-3 | Operational Information Exchange Matrix | Lists and describes information exchanged between nodes. | Network-Enterprise Model | Supported by | Report |  | NEED to assess attribution of the Interface line. Compare to need line Not at the system level. Should consider the need for an Information exchange object that is tied to the ICOM arrow, and perhaps higher level need line equivilant. |  | Not Defined | Stakeholder Exchange Diagram, IDEF 0 - ICOM Arrow | BRM, DRM
Operational View | OV-4 | Organizational Relationships Chart | Lists organizations, roles, and relationships among organizations. | People-Enterprise Model People-System Model | Supported by (graphically) | Organizational Hierarchy Diagram | Class Diagram with Actors | Simply Hierarchical. Yes with the ability to have ad-hoc associations | 2 | Org. Chart Models | Organizational Hierarchy | None
Operational View | OV-5 | Operational Activity Model | Details the activities performed and their interrelationships, including input/output relationships. | People-Enterprise Model Function-Enterprise Model | Modeled in CADM | IDEF 0 | UML Use Case Diagram, Activity Diagram | IDEF/UML/BPMN BPMN @ High-Level | 3 | Functional Models | BRM Decompostion IDEF 0 Models | BRM, DRM, ?SRM? As-Is To-Be
Operational View | OV-6a | Operational Rules Model | Identifies business rules that govern or constrain operations. | Motivation-System Model | Supported by (graphically) | Operational Activity Model Activity Hierarchy Described with Process Model or Textual Description | No equivalent product …text capture Activity Model | Business Rules Derived from BPR IDEF 3 or BPMN | 8 | IDEF0/IDEF3/BPMN | DEAR can capture rules using default SA objects | BRM
Operational View | OV-6b | Operational State Transition | Identifies sequencing and timing of activities. | Data-System Model | Supported by (graphically) | State Chart Diagram | State Chart Diagrams (composite and simple) |  |  | Not Defined | Sub-system to Information-Class and Entity mappings Component to Data-Store | BRM
Operational View | OV-6c | Operational Event Trace | Traces actions in a scenario or sequence of events. | Function-Enterprise Model | Supported by (graphically) | IDEF3 | UML Sequence Diagram | BPR Step |  | Not Defined | IDEF3/BPMN | BRM
Operational View | OV-7 | Logical Data Model | Identifies data requirements of the operational view. | Data-System Model | Supported by (graphically) | Entity Relationship Diagram | Class Diagram | Conceptual and logical models of enterprise vs. System?? What is meant by vs.?? |  | Conceptual Modeling | IDEF1X | DRM
Systems View | SV-1 | Systems Interface Description | Lists systems, system components, and their interconnections. | Network-Enterprise Model Network-Technology Constrained Model | Supported by (graphically) | Inter and IntraNodal Interfaces | Deployment Diagrams with or without components |  | 4 | System Interface diagram - Systems Location | System Interface Decomposition Diagram System Node, System, Sub System, Component Instance, and Interfaces | ??DRM, SRM?? As-Is, To Be( System and Deployment Architecture)
Systems View | SV-2 | Systems Communications Description. | Identifies system communications. | Network-Enterprise Model Function-Technology Constrained Model |  | Inter and IntraNodal Interfaces with commucication details/support | No equivalent | Could be supported through further attribution of Interface, or new object to represent a communication line that can be associated to an interface. |  | Not Defined | ??No Clear Method in DEAR??
Systems View | SV-3 | Systems-Systems Matrix. | Lists connections between individual systems in a group. | Function-Technology Constrained Model | Matrix in CADM | Report | No equivalent |  | 4 | System to System Relationship Matrix and Interface Characteristics | System to System Recommendation Matrix, System Interfaces
Systems View | SV-4 | Systems Functionality Description | Lists functions performed by individual systems and the related information flow. | Function-System Model |  | SSADM (Data Flow Diagrams) | UML Use Case Diagram, ClassDiagram |  | 4 | SRM to System Component | Interface with type of data and System Decomposition?? | DRM, SRM
Systems View | SV-5 | Operational Activity-to-Systems Function Traceability Matrix | Maps systems information back to the operational view. | Function-Technology Constrained Model |  |  | No equivalent |  | 4 | BRM F/A to Subsystem BRM to SRM | Function Activity to Sub System Complex matrix Service Component to Function Activity Matrix | BRM, SRM
Systems View | SV-6 | Systems Data Exchange Matrix | Provides detail of data moving between systems. | Function-System Model |  |  | No equivalent |  |  | ?? | System Interface Report | DRM
Systems View | SV-7 | Systems Performance Parameters Matrix. | Lists performance characteristics of individual systems. | Function-System Model | [5 empty] | ??
Systems View | SV-8 | Systems Evolution Description | Lists migration plans for systems. | Function-Technology Constrained Model |  |  | No Equivalent |  | 5 | Sequencing Plan, Implementation Plan, risk Management Plan | Transition Plans and MS./ Blueprint Document Links Architecture Migration Diagram | All Reference Models
Systems View | SV-9 | Systems Technology Forecast | Lists technologies and products that are expected to affect systems. | Network-Tech Constrained Model Data-System Model People-Enterprise Model |  |  | No Equivalent |  |  | TRM its future state | Technology Transiton Plan System Component to Tech Spec | TRM, SRM
Systems View | SV-10a | Systems Rules Model | Describes constraints on system operation imposed by design or implementation. | Motivation-Tech Constrained Model | [5 empty] | Not Defined |  | SRM, TRM, BRM
Systems View | SV-10b | Systems State Transition Description | Describes system activity sequencing and timing. | Data-System Model | [5 empty] | Not Defined
Systems View | SV-10c | Systems Event Trace Description | Describes system-specific requirements on critical event sequences. | Time-System Model | [5 empty] | Not Defined
Systems View | SV-11 | Physical Schema | Describes the physical implementation of the logical data model from the operational view. | Data-System Model |  | Physical Data Model | Class Diagram |  | 13 | Solution Architecture | Physical Data Model | DRM
Technical Standards View | TV-1 | Technical Standards Profile | Lists technical standards that apply to the architecture. | Network-Tech Constrained Model |  | Report |  |  | 4,13 (TRM Governance) | TRM and Relationship to SRM | TRM Catalog Tech Spec to Service Component Matrix | TRM,SRM
Technical Standards View | TV-2 | Technical Standards Forecast | Describes emerging or evolving standards that might apply to the architecture. | Network-Tech Constrained Model |  | Report |  |  | 4,13 (TRM Governance) | TRM and Relationship to SRM | Tech Spec to Service Component Matrix | TRM,SRM

## Zachman-DODAF
| C | 1 | 2 | 3 | 4 | 5 | 6
R | Abstractions > \/ Perspectives | Data | Function | Network | People | Time | Motivation
1 | Scope |  | OV-1 | OV-2 |  |  | AV-1
2 | Enterprise Model |  | OV-5 OV-6c | OV-3, SV-1, SV-2 | OV-5 SV-9, OV-4
3 | System Model | OV-6B SV-10b OV-7 SV-11 SV-9 | SV-4, SV-6, SV-7 |  | OV-4 | SV-10c | OV-6a
4 | Tech Constrained Model |  | SV-2, SV-3 SV-5, SV-8 | SV-1, TV-1, TV-2, SV-9 |  |  | SV-10a
5 | Detailed Representations | AV-2
6 | Functioning Enterprise

## DODAF-Zachman
DODAF View Type | DODAF Product Code | DODAF Product Name | DODAF Product Description | Zachman
All View | AV-1 | Overview and Summary Information | Details scope, purpose, environment, and other summary-level formation for an architecture description. | Motivation-Scope Model
All View | AV-2 | Integrated Dictionary | Provides definitions of all terms used in all products. | Data-Detailed Representations Model
Operational View | OV-1 | Operational Concept Graphic | Provides a graphical and textual description of the operational concept. | Function-Scope Model
Operational View | OV-2 | Operational Node Connectivity Description. | Lists the operational nodes, activities performed at each node, connectivity, and information needs between nodes. | Network-Scope Model
Operational View | OV-3 | Operational Information Exchange Matrix | Lists and describes information exchanged between nodes. | Network-Enterprise Model
Operational View | OV-4 | Organizational Relationships Chart | Lists organizations, roles, and relationships among organizations. | People-Enterprise Model People-System Model
Operational View | OV-5 | Operational Activity Model | Details the activities performed and their interrelationships, including input/output relationships. | People-Enterprise Model Function-Enterprise Model
Operational View | OV-6a | Operational Rules Model | Identifies business rules that govern or constrain operations. | Motivation-System Model
Operational View | OV-6b | Operational State Transition | Identifies sequencing and timing of activities. | Data-System Model
Operational View | OV-6c | Operational Event Trace | Traces actions in a scenario or sequence of events. | Function-Enterprise Model
Operational View | OV-7 | Logical Data Model | Identifies data requirements of the operational view. | Data-System Model
Systems View | SV-1 | Systems Interface Description | Lists systems, system components, and their interconnections. | Network-Enterprise Model Network-Technology Constrained Model
Systems View | SV-2 | Systems Communications Description. | Identifies system communications. | Network-Enterprise Model Function-Technology Constrained Model
Systems View | SV-3 | Systems-Systems Matrix. | Lists connections between individual systems in a group. | Function-Technology Constrained Model
Systems View | SV-4 | Systems Functionality Description | Lists functions performed by individual systems and the related information flow. | Function-System Model
Systems View | SV-5 | Operational Activity-to-Systems Function Traceability Matrix | Maps systems information back to the operational view. | Function-Technology Constrained Model
Systems View | SV-6 | Systems Data Exchange Matrix | Provides detail of data moving between systems. | Function-System Model
Systems View | SV-7 | Systems Performance Parameters Matrix. | Lists performance characteristics of individual systems. | Function-System Model
Systems View | SV-8 | Systems Evolution Description | Lists migration plans for systems. | Function-Technology Constrained Model
Systems View | SV-9 | Systems Technology Forecast | Lists technologies and products that are expected to affect systems. | Network-Tech Constrained Model Data-System Model People-Enterprise Model
Systems View | SV-10a | Systems Rules Model | Describes constraints on system operation imposed by design or implementation. | Motivation-Tech Constrained Model
Systems View | SV-10b | Systems State Transition Description | Describes system activity sequencing and timing. | Data-System Model
Systems View | SV-10c | Systems Event Trace Description | Describes system-specific requirements on critical event sequences. | Time-System Model
Systems View | SV-11 | Physical Schema | Describes the physical implementation of the logical data model from the operational view. | Data-System Model
Technical Standards View | TV-1 | Technical Standards Profile | Lists technical standards that apply to the architecture. | Network-Tech Constrained Model
Technical Standards View | TV-2 | Technical Standards Forecast | Describes emerging or evolving standards that might apply to the architecture. | Network-Tech Constrained Model